## Summary
OudhTrade — Admin screens design tracker (onboarding)
Companion to "Admin UX Design Brief — Onboarding". Counts below update from the other sheets.
Screens by design status
Status | Screens | Share
To design | 25 | 100%
In progress | 0 | 0%
In review | 0 | 0%
Done | 0 | 0%
Total | 25 | 100%
Screens by pattern
Pattern | Screens | Done
P1 Queue + case review | 9 | 0
P2 Settings editor | 9 | 0
P3 List management | 5 | 0
P4 Look-up | 2 | 0
Total | 25 | 0
Screens by priority (P1 = design first)
Priority | Screens | Done
P1 | 5 | 0
P2 | 11 | 0
P3 | 9 | 0
Total | 25 | 0
Other progress
Item | Done | Of
Patterns and shell done | 0 | 6
New components done | 0 | 12
Open questions answered | 6 | 8
Legend
Yellow cells | Inputs for the designer and product owner: Screens — Design status, Figma link, Designer notes, Product owner notes, Due date; Patterns — Status, Designer notes; New components — Status, Figma link; Open questions — Answer, Answered on.
Design status | Pick from the list: To design · In progress · In review · Done.
Priority | Suggested design order (P1 first). Release labels are planning hints only.
Brief section | Section of the Word brief with the screen page (for example "6 · AD-01").

## Screens
ID | Screen | Pattern | Users | Priority | Spec section | Brief section | Design status | Figma link | Designer notes | Product owner notes | Due date
AD-01 | A — Verification review | P1 | Moderator (Senior Moderator for escalations) | P1 | M03-6 §16.1 | 6 · AD-01 | To design
AD-02 | Video-call ID checks | P1 | Moderator | P2 | M03-6 §16.18 | 6 · AD-02 | To design
AD-03 | Sanctions batch and match review | P1 | Senior Moderator | P3 | M03-6 §16.13 | 6 · AD-03 | To design
AD-04 | B — Role change decision | P1 | Admin, Super Admin | P2 | M03-6 §16.3 | 6 · AD-04 | To design
AD-05 | C — Farm visit review | P1 | Moderator | P1 | M03-6 §16.4 | 6 · AD-05 | To design
AD-06 | Recovery and number-reclaim review | P1 | Admin, Super Admin (Support: open, note) | P2 | M02-6 §20.2 | 6 · AD-06 | To design
AD-07 | Staff-awarded badge applications | P1 | Moderator decides; Admin views holders | P3 | M03-6 §16.6 | 6 · AD-07 | To design
AD-08 | Lab accreditation review | P1 | Moderator | P3 | M03-6 §16.19 | 6 · AD-08 | To design
AD-09 | Partner programme review | P1 | Admin | P3 | M03-6 §16.20 | 6 · AD-09 | To design
AD-10 | E1 — Document checklists | P2 | Admin draft, Super Admin approve (high impact) | P1 | M03-6 §16.7 | 6 · AD-10 | To design
AD-11 | E2 — Business ID rules per country | P2 | Admin draft, Super Admin approve (high impact) | P2 | M03-6 §16.8 | 6 · AD-11 | To design
AD-12 | E3 — Rejection reasons | P2 | Admin draft, other Admin approve | P2 | M03-6 §16.9 | 6 · AD-12 | To design
AD-13 | E4 — Setup card items per role | P2 | Admin draft, other Admin approve | P2 | M03-6 §16.10 | 6 · AD-13 | To design
AD-14 | E5 — Role change paths and capability bands | P2 | Paths: Super Admin approve; bands: other Admin approve | P3 | M03-6 §16.11 | 6 · AD-14 | To design
AD-15 | E6 — Badge types | P2 | Admin draft, Super Admin approve (high impact) | P3 | M03-6 §16.12 | 6 · AD-15 | To design
AD-16 | Country table | P2 | Admin draft, Super Admin approve (high-impact fields) | P2 | M01-6 §12.4 | 6 · AD-16 | To design
AD-17 | Throw-away email domain list | P2 | Admin draft, other Admin approve | P3 | M02-6 §20.7 | 6 · AD-17 | To design
AD-18 | Changes / approvals | P2 | Super Admin, Admin (Finance: own drafts) | P2 | M01-6 §12.1 | 6 · AD-18 | To design
AD-19 | Invitations admin | P3 | Admin | P1 | M02-6 §20.3 | 6 · AD-19 | To design
AD-20 | Field agents | P3 | Admin | P1 | M03-6 §16.16 | 6 · AD-20 | To design
AD-21 | Delegations overview | P3 | Admin | P3 | M02-6 §20.4 | 6 · AD-21 | To design
AD-22 | Farm-visit queue by district | P3 | Moderator, Admin | P2 | M03-6 §16.17 | 6 · AD-22 | To design
AD-23 | Agent and FPO quality re-checks | P3 | Moderator, Admin | P3 | M03-6 §16.15 | 6 · AD-23 | To design
AD-24 | Account lookup | P4 | Super Admin, Admin, Moderator, Support (read-only) | P2 | M02-6 §20.1 | 6 · AD-24 | To design
AD-25 | Support profile and case view | P4 | Support (read-only) | P2 | M03-6 §16.21 | 6 · AD-25 | To design

## Patterns
ID | Pattern | Parts to design | Used by | Brief section | Status | Designer notes
Shell | Admin console shell | Top bar (search, queue counts, environment label, profile) · left menu in five groups · page header · 1440 frame | All screens | 3 | To design
P1 | Queue + case review | Queue table (columns, filters, tabs, due-time countdown, flags, fast lane first) · case view (summary header, tabs, documents, history, internal notes) · secure document viewer (watermark, zoom, rotate, page list, "Every view is logged") · decision bar (accept / reject per document with reason and message preview, ask a question, hold, decide) · reason dialog · edit-conflict banner | AD-01, AD-02, AD-03, AD-04, AD-05, AD-06, AD-07, AD-08, AD-09 | 4.1 | To design
P2 | Settings editor | List with status chips · draft edit with checks as you type · Preview impact · Send for approval (reason) · two-level approval · Publish now / Schedule · History · Roll back · "High impact" chip · edit-conflict banner | AD-10, AD-11, AD-12, AD-13, AD-14, AD-15, AD-16, AD-17, AD-18 | 4.2 | To design
P3 | List management | Table with filters, search and tabs · add / edit side panel · status chips · end / revoke / suspend with reason · bulk upload with preview where relevant | AD-19, AD-20, AD-21, AD-22, AD-23 | 4.3 | To design
P4 | Look-up | One search box · result rows with masked contacts · reason dialog before opening · read-only summary with tabs · "Your view is logged" banner · masked value with Show (reason, 60 s, logged) where allowed | AD-24, AD-25 | 4.4 | To design
States | Common states | Loading · empty · not allowed · validation error · server error · load error · edit conflict · reason dialog | All screens | 4.5 | To design

## New components
Component | Used by | What it does | Status | Figma link
Queue table row | AD-01–AD-09, AD-22, AD-23 | Compact row with flags, fast-lane mark, due-time countdown and status chip | To design
Due-time countdown | AD-01–AD-09, AD-19, AD-22 | "Due in {h} h" / "Overdue" with icon and words; turns red at 80 % of the target | To design
Document viewer | AD-01, AD-02, AD-04–AD-08 | Watermark with reviewer name, time and case number; zoom, rotate, page list; "Every view is logged" | To design
Decision bar | AD-01–AD-09 | Sticky bar at the bottom of a case; buttons change per screen | To design
Reason dialog | All screens | Reason list and/or text (at least 10 characters); names the action and who is told | To design
Approval bar | AD-10–AD-18 | Status chip, "High impact" chip, Send for approval / Approve / Reject / Publish / Schedule | To design
Diff / preview panel | AD-10–AD-18 | Old → new values marked "Added", "Changed", "Retired" with icon and word; counts; example | To design
Version history list | AD-10–AD-18 | Version, status, editor, approver, date, reason; Compare; Roll back to this version | To design
Masked value with Show | AD-06, AD-19, AD-21, AD-24 | Masked phone or email; Show (where allowed) asks a reason, shows 60 s, is logged | To design
Checklist ticks | AD-02, AD-05, AD-06, AD-08 | Required ticks that unlock the decision button | To design
Photo location panel | AD-01, AD-05 | Reason first; small map, coordinates, distance; "This view is recorded with your reason." | To design
Read-only banner | AD-24, AD-25 | "Read-only · Your view is logged" / "Your view is logged" | To design

## Open questions
# | Question | Owner | Answer | Answered on
1 | Dark mode for staff screens? The UX-UI Foundation (U8) says no dark mode in V1; confirm this also applies to the admin console. | Product owner | Decided 26 Sep: light mode only for the console. | 26 Sep 2026
2 | Table density: compact rows by default with a "comfortable" switch, or compact only? | Designer + product owner | Decided 26 Sep: compact tables by default (no switch). | 26 Sep 2026
3 | Can one farmer be a member of several FPOs at the same time? (open product question; affects S15, AD-19 and AD-23) | Product owner | Decided 26 Sep: yes, several FPOs allowed; each link is confirmed separately; any one confirmed link gives Verified farmer. | 26 Sep 2026
4 | Final list of keyboard shortcuts for queues (proposal in Section 3.3). | Designer + tech lead
5 | Video-call ID check: is the video shown inside the case view or in the supplier’s own window next to it? (supplier not chosen yet) | Product owner + tech lead
6 | Staff-awarded badge applications: the brief listed "Admin" as the user, but M03-6 §16.6 says a Moderator decides them on screen A. This brief follows M03-6. Confirm. | Product owner | Decided 26 Sep: a Moderator decides (AD-01 Badge applications tab); Admin only creates badge types (AD-15). | 26 Sep 2026
7 | Settings editors are built in the Configuration Console (M16) and staff screens in the Operations Console (M15). This brief assumes one shared shell look with the Settings menu group. Confirm. | Product owner + designer | Decided 26 Sep: one shared console shell; Settings is a menu group. | 26 Sep 2026
8 | Should each Moderator have a personal queue ("Assigned to me") and can cases be assigned, or does everyone pick from one shared queue? | Product owner | Decided 26 Sep: one shared queue (fast lane first, then due time); a Moderator can pick a case ("Assigned to me"); a Senior Moderator can assign cases to others. | 26 Sep 2026